## Overview
SalesGenie AI — Sprint Plan & Effort Tracker (All 4 Milestones)
AI Sales Assistant & Lead Intelligence Platform
Hours per working day (assumption) | 8 | ← edit this cell; all sprint sheets recalculate automatically
Note: hours = task duration in days × hours/day above. For tasks with two co-owners (e.g. “Frontend Developer + AI/ML Engineer”), each named owner is credited the full task hours in the Hours Summary sheet (i.e. hours are not split between them) — both people are actively engaged for the task's full duration.
Milestone | Day Range | Start Date | End Date | Modules Covered | Evaluation Criteria
Milestone 1 | Day 4-14 | 2026-07-18 | 2026-07-28 | Module 1 (Lead Management) + Module 2 (Lead Intelligence) | Manage/analyze ≥95% of prospect records; accurate company insights & lead intelligence
Milestone 2 | Day 15-20 | 2026-07-29 | 2026-08-03 | Module 3 (AI Outreach) + Module 4 (Lead Scoring) | Lead scoring accuracy ≥85%; personalized outreach content for multiple industries
Milestone 3 | Day 21-25 | 2026-08-04 | 2026-08-08 | Module 5 (CRM Integration & Conversation Intelligence) | CRM integration functions correctly; sales conversation summaries generated successfully
Milestone 4 | Day 26-30 | 2026-08-09 | 2026-08-13 | Module 6 (Dashboard & Analytics) + Full Integration | Dashboard fully operational; end-to-end workflow functional; response time <5 sec; satisfaction ≥85%

## Sprint 1 (Milestone 1)
SalesGenie AI — Sprint 1 (Milestone 1)
Day(s) | Task | Owner (Role) | Duration (Days) | Hours | Deliverable
Day 4 | Design ER diagram & finalize PostgreSQL schema (Leads, Users, CRM_Sync_Logs) | Database/DevOps Engineer | 1 | 8 | Finalized schema + migrations
Day 5 | Design Streamlit wireframes (Leads, Outreach, Conversations, Dashboard tabs) | Frontend Developer | 1 | 8 | UI wireframes
Day 6 | Design LangGraph agent architecture (Research, Qualification, Outreach, CRM agents) | AI/ML Engineer | 1 | 8 | Agent architecture diagram
Day 7-8 | Build prospect CRUD APIs (module1_leads.py) | Backend Developer | 2 | 16 | FastAPI CRUD endpoints
Day 8-9 | Build lead import (CSV/manual) with de-duplication | Backend Developer | 2 | 16 | Lead import module
Day 9-10 | Build Streamlit 'Leads' tab (search list + detail panel) | Frontend Developer | 2 | 16 | Leads UI screen
Day 10-11 | Build company profile analysis service (module2_intelligence.py) | AI/ML Engineer | 2 | 16 | Company analysis service
Day 11-12 | Build AI qualification scoring engine + Lead Intelligence card | AI/ML Engineer | 2 | 16 | Qualification score API
Day 12 | Integrate Lead Intelligence into Leads UI (score badge, insights panel) | Frontend Developer + AI/ML Engineer | 1 | 8 | Lead Intelligence UI panel
Day 13 | Unit test lead CRUD + review qualification score accuracy | QA Engineer | 1 | 8 | Milestone 1 test report
Day 14 | Milestone 1 review: ≥95% records manageable, insights accuracy check; sign-off | Project Lead + QA Engineer | 1 | 8 | Milestone 1 sign-off
| TOTAL |  | 16 | 128

## Sprint 2 (Milestone 2)
SalesGenie AI — Sprint 2 (Milestone 2)
Day(s) | Task | Owner (Role) | Duration (Days) | Hours | Deliverable
Day 15-16 | Build AI email/outreach generation service (prompt templates per industry) | AI/ML Engineer | 2 | 16 | Outreach generation API
Day 16-17 | Build Streamlit 'Outreach' tab: AI Email Generator with edit-before-send | Frontend Developer | 2 | 16 | Outreach UI screen
Day 17-18 | Implement lead scoring & conversion probability model | AI/ML Engineer + Backend Developer | 2 | 16 | Lead scoring engine
Day 18-19 | Build recommendation engine: follow-up timing, channel mix, content strategy | AI/ML Engineer | 2 | 16 | Recommendation engine service
Day 19 | Integrate Lead Score + Outreach Strategy cards into Outreach UI | Frontend Developer | 1 | 8 | Outreach Strategy UI panel
Day 20 | Validate lead scoring accuracy (≥85%), test outreach across 3+ industries; sign-off | QA Engineer + Project Lead | 1 | 8 | Milestone 2 sign-off
| TOTAL |  | 10 | 80

## Sprint 3 (Milestone 3)
SalesGenie AI — Sprint 3 (Milestone 3)
Day(s) | Task | Owner (Role) | Duration (Days) | Hours | Deliverable
Day 21-22 | Build FastAPI endpoints for CRM integration (Salesforce/HubSpot schema mapping) | Backend Developer | 2 | 16 | CRM integration API
Day 22-23 | Implement CRM sync logic (contacts, activities, deal stages) + sync logs | Backend Developer + Database/DevOps Engineer | 2 | 16 | CRM sync service
Day 23-24 | Build meeting/call summarization (key points + action items) via LLM | AI/ML Engineer | 2 | 16 | Conversation summarization service
Day 24 | Build Streamlit 'Conversations' tab: CRM Sync Status + Meeting Summary + Activity feed | Frontend Developer | 1 | 8 | Conversations UI screen
Day 25 | Test CRM sync across workflows, validate summarization output quality; sign-off | QA Engineer + Project Lead | 1 | 8 | Milestone 3 sign-off
| TOTAL |  | 8 | 64

## Sprint 4 (Milestone 4)
SalesGenie AI — Sprint 4 (Milestone 4)
Day(s) | Task | Owner (Role) | Duration (Days) | Hours | Deliverable
Day 26-27 | Build Sales Analytics API (conversion rate, pipeline value, sales cycle KPIs) | Backend Developer | 2 | 16 | Analytics API
Day 26-27 | Build Dashboard UI + Kanban-style pipeline view | Frontend Developer | 2 | 16 | Dashboard tab (Streamlit)
Day 27 | Build automated follow-up recommendation panel | AI/ML Engineer + Frontend Developer | 1 | 8 | Follow-up panel
Day 28 | End-to-end integration of all 6 modules; performance tuning (<5 sec target) | Full Team | 1 | 8 | Integrated end-to-end build
Day 29 | Full regression testing, UAT with sample users, capture satisfaction score | QA Engineer | 1 | 8 | UAT report + test sign-off
Day 30 | Deploy to production/staging (Docker), final demo, documentation handover, retrospective | Full Team | 1 | 8 | Deployed app + final demo + closure doc
| TOTAL |  | 8 | 64